## Instructions
AUDIT CHECKLIST INSTRUCTIONS
Provided by COLBI Technologies, Inc.
Example of Audit File with Sub Files - on ICON view you can see if any items are in the files.
It is always best to begin a project with the end in mind. Not just the final project concept, but passing the audit as well. To that end, COLBI is providing this checklist for retaining the documents that will be required for the final audit per the new Grant Agreement and the new Audit Guidlines.
The checklists are designed as a lead sheet for a binder that can be handed to your auditor at the end of the project. This is an approach that we have used for years and we have highlighted the things that are new, by shading them green.
The list tells you the things you will need to collect. This collection works best if you do it as the project progresses. It is much more difficult if you wait until the end and try to find all these materials.
The tabs are designed for numbered binder dividers, but you can number them with post it notes as tabs (much cheaper!) Filling in the date of the doc provides a time reference and also indicates that the item has been put in the binder. The * column is for the initials of the person who added it.
The alternate version is for use as a digital checklist which can reside on your desktop of in the file section. The key is to be continuously checking that you have been collecting and storing the documents as they occur.
The 18 column indicates that this information will be requested by OPSC at either the 18 Month Substantial Review or at Close Out. The A column indicates that it is an Audit item.
Within the Document to File folder you can place the required individual 'doc to file' items.
Some of our clients have added a column with the name of the person responsible for that line item. And someone needs to own reponsibility to remind people to be filing these items as the project occurs. It could be a monthly meeting reminder, or a quarterly check of the "books" to verify they are up to date per the status of the project.
One of the good things in the new audits is that you are now allowed to retain the record digitally. This list can be managed as a binder or a file folder in your storage system, with a sub folder for each "tab." Then the item can be saved in the appropriate sub folder. (Always use the latest checklist to create your folders, we update the attached list but this illustration does not get updated.)
The entire file can be saved to a jump drive and handed to your auditor or loaded to their drop box. At 18-Month Substantial Completion or project closeout review, specific files can be copied to OPSC.
It might be best to build it once as a template, then copy it into where you save documents for a particular project. Then begin to customize it and populate it for that project, retaining your blank template to use for additional projects. That should save some time.
The challenge digitally is being able to see where your gaps are. If you use the ICON view, you will be able to see if anything is in the file.
The right answer as to whether you use a binder or do digital files may depend on how big your program is and what makes sense to the person actually doing the work. Always maintain a backup.
We hope this information is helpful!
If you notice anything we have missed or that would be helpful to others, please let us know.
leboggs@colbitech.com
Some additional considerations not on the checklist:
1. OPSC past updates to DLOPE require that the following object codes be established to track specific Site Expenditures as follows:
a. 61xx-POESA/PEA Cost (Environmental assessment)
b. 61xx-DTSC Fees
c. 61xx-Hazardous Waste Removal
2. Operational expenses are not to be included in the 50-06. (Operational object codes start with 5xxx) Audit expenses are not to be included in DLOPE.
3. F&E expenditures are not to be included in DLOPE unless approved in specific State Grant Agreement
4. 61xx expenditures are not reportable in DLOPE unless they are specified in the State Site Grant Agreement.
5. Object 6170 and above is used to track Site Improvement Expenditures not related to original site purchase.
6. Project Savings declared on the State Funded project will delay final 50-06 reporting until such time as all expenditures
for that savings and interest earned can be reported in the High Priority Project using the project savings.

## 18 Mo and Audit Cklist
PROJECT TYPE and NUMBER: |  |  | OPSC NUMBER: |  |  |  |  | PROJECT TYPE and NUMBER: |  |  | OPSC NUMBER:
Category |  | Item | 18 | A | Date of Doc | Tab | T | Category |  | Item | 18 | A | Date of Doc | Location
Site | - | CDE Site Approval Letter |  |  |  | 1 |  | Site | - | CDE Site Approval Letter
New Sites only | - | Proof of Acreage Purchased |  |  |  | 2 |  | New Sites only | - | Proof of Acreage Purchased
Site | - | CEQA Compliance Board Action |  |  |  | 3 |  | Site | - | CEQA Compliance Board Action
Site | - | DTSC No Further Action Letter |  |  |  | 4 |  | Site | - | DTSC No Further Action Letter
Planning | - | Architect Qualifications Appraisal & Agreement, with evidence of competitive selection |  |  |  | 5 |  | Planning | - | Architect Qualifications Appraisal & Agreement, with evidence of competitive selection
Planning | - | Architect Amendments to Contract |  |  |  | 6 |  | Planning | - | Architect Amendments to Contract
Planning | - | Architect Final Billing |  |  |  | 7 |  | Planning | - | Architect Final Billing
Planning | - | Construction Manager Qualifications & Agreement |  |  |  | 8 |  | Planning | - | Construction Manager Qualifications & Agreement
Planning | - | Surveyor Qualifications Appraisal & Agreement |  |  |  | 9 |  | Planning | - | Surveyor Qualifications Appraisal & Agreement
Planning | - | Engineer's Qualifications Appraisal & Agreement |  |  |  | 10 |  | Planning | - | Engineer's Qualifications Appraisal & Agreement
Planning | - | CDE Plan Approval Letter |  |  |  | 11 |  | Planning | - | CDE Plan Approval Letter
Planning | - | Local Plan Approval (Submittal For Review And Comment) |  |  |  | 12 |  | Planning | - | Local Plan Approval (Submittal For Review And Comment)
Planning | - | DSA Number And Plan Approval Letter |  |  |  | 13 |  | Planning | - | DSA Number And Plan Approval Letter
Construction | - | Bid Advertisement |  |  |  | 14 |  | Construction | - | Bid Advertisement
Construction | - | Evidence of DVBE compliance effort |  |  |  | 15 |  | Construction | - | Evidence of DVBE compliance effort
Construction | - | Construction Bid Summary and Delivery Method |  |  |  | 16 |  | Construction | - | Construction Bid Summary and Delivery Method
Construction | - | Notice To Proceed |  |  |  | 17 |  | Construction | - | Notice To Proceed
Construction | - | Inspector Qualifications Appraisal & Aggreement |  |  |  | 18 |  | Construction | - | Inspector Qualifications Appraisal & Aggreement
Construction | - | Construction Contract With Board Award |  |  |  | 19 |  | Construction | - | Construction Contract With Board Award
Construction | - | Change Orders With DSA Stamps (Or Architect Letter) |  |  |  | 20 |  | Construction | - | Change Orders With DSA Stamps (Or Architect Letter)
Construction | - | Final Construction Billing |  |  |  | 21 |  | Construction | - | Final Construction Billing
Construction | - | Notice of Completion |  |  |  | 22 |  | Construction | - | Notice of Completion
Mod Doc to File | - | Verify Plans Reflect Zero New Square Footage |  |  |  | 23 |  | Mod Doc to File | - | Verify Plans Reflect Zero New Square Footage
Mod Doc to File | - | Verify Site Dev Costs Are Only For Replacement/Repair |  |  |  | 24 |  | Mod Doc to File | - | Verify Site Dev Costs Are Only For Replacement/Repair
Doc to File | - | Compare Number of CRs on Plans to the 50-04 |  |  |  | 25 |  | Doc to File | - | Compare Number of CRs on Plans to the 50-04
Doc to File | - | If shared project, Prorated Split Basis |  |  |  | 26 |  | Doc to File | - | If shared project, Prorated Split Basis
Doc to File | - | Funding source plan |  |  |  | 27 |  | Doc to File | - | Funding source plan
Doc to File | - | If applicable, the High Priority Project designation |  |  |  | 28 |  | Doc to File | - | If applicable, the High Priority Project designation
Doc to File | - | Routine Restricted Maint. Account 3% Verification (Each Yr) |  |  |  | 29 |  | Doc to File | - | Routine Restricted Maint. Account 3% Verification (Each Yr)
State | - | SAB Agenda items related to the project |  |  |  | 30 |  | State | - | SAB Agenda items related to the project
State | - | SAB 50-04 And Amount Spent On Hard Costs |  |  |  | 31 |  | State | - | SAB 50-04 And Amount Spent On Hard Costs
State | - | SAB 50-05 And Occupancy Date |  |  |  | 32 |  | State | - | SAB 50-05 And Occupancy Date
State | - | Advisory Letter(s), if any |  |  |  | 33 |  | State | - | Advisory Letter(s), if any
State | - | SAB 50-06 Final and DLOPE |  |  |  | 34 |  | State | - | SAB 50-06 Final and DLOPE
Procedure | - | Dept Procedure for handling SFP transactions |  |  |  | 35 |  | Procedure | - | Dept Procedure for handling SFP transactions
Verification | - | CSAM Compliant Coding Structure |  |  |  | 36 |  | Verification | - | CSAM Compliant Coding Structure
Fin Hardship | - | Evidence of liquidating encumbrances |  |  |  | 37 |  | Fin Hardship | - | Evidence of liquidating encumbrances
Note: All contracts and payment records for the project will need to be retained for audit. | [7 empty] | Note: All contracts and payment records for the project will need to be retained for audit.

## Em Domain Cklst
EMINENT DOMAIN AND RELOCATION COSTS
Note: You may provide Page 2 of the DLOPE to your relocation consultant and require
that they provide the summary report in the manner that you will need it for OPSC.
You will need to keep a complete record for each APN/AIN.
If you do not do Condemnation/Relocation, you will not need to do page 2 of the DLOPE for the 50-06 or audit.